## Sheet1
Meeting # | Date | Details | Members | Member Key | Cade | W
1 | 2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales | W,X,T,R,B,M |  | Carolyn | X
2 | 2018-01-28 | SRS documentation Delegated user stories and use case diagrams to team members | T,W,X,B |  | Andre | M
3 | 2018-02-08 | SRS documentation | W,M,T |  | Turner | T
4 | 2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed details of security and encryption for program General way to program project Layout of different screens of project SRS documentation | W,X,T,R,B |  | Riggs | R
5 | 2018-02-20 | Encryption - Implementation of 256-bit in Python | M, R |  | Mayur | B
6 | 2018-02-23 | Encryption - Implementation of 256-bit in Java - Work in progress | M, R
7 | 2018-02-26 | Encryption - Implementation of 256-bit in Java - Finalizing Password Encryption | M, R