## Sheet1
ID | Story | Sprint | Priority | Status | Story Points
10 | As a small business owner, I want to be able to predict the amount of sales on a certain day so that I can schedule employees accordingly | 4,5 | 5 | IP | 8
11 | As a small business owner,I want to be able to predict the amount of income on a certain day so that I can account for potential sales | 4,5 | 4 | IP | 8
12 | As a small business owner,I want to be able to input the total revenue made for the day into the database upon closing so that I can use that data to update the accuracy of the software | 4,5 | 3 | IP | 6
13 | As a small business owner,I want to use my sales reports from past years so that I can get an estimate prediction of future sales | 4,5 | 2 | IP | 4
14 | As a small business owner,I want to use sales report from past years so that I can see requirements needed to hit specific sales margins |  | 1 | W | 4
15 | As a small business owner,I want to input any date into the software so that I can review data over my company for that specific date. | 1,2 4,5 | 6 | IP | 5
16 | As a small business owner, I want to be able to create sub accounts, so that I can keep access to certain data restricted. | 1,2 4,5 | 7 | D | 2
17 | As a small business owner, I want to be able to log in into my account, so that I can easily access my data. | 1,2 4,5 | 8 | D | 2
18 | As a small business owner, I want to be able to set certain parameters so that i can easily view specific data | 4,5 | 9 | IP | 2
19 | As a small business owner I want to be able to input sales reports from past years so they can be used in the application |  | 11 | W | 6
20 | As a small business owner I want to be able to have an unrestricted admin account to access all data | 1,2 | 10 | D | 1
.
Total |  |  |  |  | 48