## Andre Manz
Date | Details
2018-01-23 | Approached my employer with the idea for a trend predicition software that uses projected sales figures to predict crowds and staffing requirements
2018-01-28 | Created Google Drive, Began work on SRS documentation, Worked on User Story and Case Diagrams as directed by Scrum Master
2018-02-08 | Clarified the program requirements to the group based on the feedback from my employer. Continued work on SRS
2018-02-09 | Specified how database will be stored, formatted and arranged, Discussed details of security and encryption for program, General way to program project, Layout of different pages of project, SRS documentation
2018-02-13 | Finishing up the first version of the SRS.

## Mayur Bhakta
Date | Details
2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales
2018-01-28 | Created Google Drive SRS documentation Worked on user stories and use cases delegated by Scrum Master.
2018-02-08 | SRS documentation
2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed details of security and encryption for program General way to program project Layout of different screens of project SRS documentation
2018-02-12 | Start developing GUI for the application.
2018-02-13 | Deliverable 1 documentation review.

## Aaron Turner
Date | Details
2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales
2018-01-28 | Created Google Drive SRS documentation Delegated user stories and use case diagrams to team members
2018-02-08 | SRS documentation
2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed details of security and encryption for program General way to program project Layout of different screens of project SRS documentation
2018-02-12 | Front End: GUI screen development
2018-02-13 | Documentation for Deliverable 1

## Aaron Riggs
Date | Details
2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales
2018-01-28 | Did user stories and use case diagrams.
2018-02-08 | SRS work
2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed implementation of security and encryption General implementation of project SRS work

## Xujia Wu(Carolyn)
Date | Details
2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales
2018-01-28 | Created Google Drive SRS documentation Completed user stories and use case diagrams.
2018-02-08 | SRS documentation
2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed details of security and encryption for program General way to program project Layout of different screens of project SRS documentation
2018-02-12 | Front End meet for designing GUI screen
2018-02-13 | work on Deliverable 1's Documentation

## Michael (Cade) Wall
Date | Details
2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales
2018-01-28 | Created Google Drive SRS documentation Delegated user stories and use case diagrams to team members
2018-02-08 | SRS documentation
2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed details of security and encryption for program General way to program project Layout of different screens of project SRS documentation
2/20/18 | 4 hours database connection
2/19/18 | 3 hours upload into python and parsing data