## Sheet1
Meeting # | Date | Details | Members | Member Key | Cade | W
1 | 2018-01-23 | General overview of different potential ideas and topics of program Decided on implementing the idea of helping Andre's employer by making use of sales data for forecasting and predicting sales | W,X,T,R,B,M |  | Carolyn | X
2 | 2018-01-28 | SRS documentation Delegated user stories and use case diagrams to team members | T,W,X,B |  | Andre | M
3 | 2018-02-08 | SRS documentation | W,M,T |  | Turner | T
4 | 2018-02-09 | Dicussed and decided to break project up into 3 separate parts: Frontend, Encryption, Backend Specified how database will be stored, formatted and arranged Discussed details of security and encryption for program General way to program project Layout of different screens of project SRS documentation | W,X,T,R,B |  | Riggs | R
5 | 2018-02-20 | Encryption - Implementation of 256-bit in Python | M, R |  | Mayur | B
| 2018-02-20 | Backened - search for and properly set up python for mysql | w
| 2018-02-22 | Backened - search for and properly set up python for mysql/begin averaging calculations | w
6 | 2018-02-23 | Encryption - Implementation of 256-bit in Java - Work in progress | M, R
7 | 2018-02-26 | Encryption - Implementation of 256-bit in Java - Finalizing Password Encryption | M, R
8 | 2018-02-23 | Frontend - Improved overall design, tested connection with a test database. | B, X, T
9 | 2018-02-26 | Frontend - Improved overall design, returned values from database, and validate username and password with the test database. | B, X
| 2018-02-26 | backend - translate python into java due to database errors caused in python parsing | w