## SprintBacklog1
ID | Story | Story Type | Story Points | Tasks | Week 1 (1/25/2018) | Week 2 (2/05/2018)
10 | As a small business owner, I want to be able to predict the amount of sales on a certain day so that I can schedule employees accordingly | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
11 | As a small business owner,I want to be able to predict the amount of income on a certain day so that I can account for potential sales | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
12 | As a small business owner,I want to be able to input the total revenue made for the day into the database upon closing so that I can use that data to update the accuracy of the software | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
13 | As a small business owner,I want to use my sales report from past years so that I can get an estimate prediction of future sales | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
14 | As a small business owner,I want to use sales report from past years so that I can see requirements needed to hit specific sales margins | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
15 | As a small business owner,I want to input any date into the software so that I can review data over my company for that specific date. | F:KA |  | *Create a python process to upload the information from excel into the mysql database(backend) | Cade:4 Andre: Turner: Mayur: Riggs: Carolyn: | Cade:4 Andre: Turner: Mayur: Riggs: Carolyn:
16 | As a small business owner, I want to be able to create sub accounts, so that I can keep access to certain data restricted. | NF:KA |  | *Created account creation screen | Cade: Andre: Turner: 2 Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
17 | As a small business owner, I want to be able to log in into my account, so that I can easily access my data. | F:KA |  | *Created sign into account screen | Cade: Andre: Turner: Mayur: Riggs: Carolyn: 2 | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
18 | As a small business owner, I want to be able to set certain parameters so that i can easily view specific data | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
19 | As a small business owner I want to be able to input sales reports from past years so they can be used in the application | NF:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
20 | As a small business owner I want to be able to have an unrestricted admin account to access all data | F:TW |  | *Implemented a local account database *Inputted pre-existing manager account | Cade: Andre: Turner: Mayur: 2 Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
Documentation
| SRS |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Platform |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| SprintReview |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Product Backlog |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Focus Group |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Team Member Report |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:

## SprintBacklog2
ID | Story | Story Type | Story Points | Tasks | Week 1 (2/12/2018) | Week 2 (2/19/2018)
10 | As a small business owner, I want to be able to predict the amount of sales on a certain day so that I can schedule employees accordingly | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
11 | As a small business owner,I want to be able to predict the amount of income on a certain day so that I can account for potential sales | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
12 | As a small business owner,I want to be able to input the total revenue made for the day into the database upon closing so that I can use that data to update the accuracy of the software | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
13 | As a small business owner,I want to use my sales report from past years so that I can get an estimate prediction of future sales | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
14 | As a small business owner,I want to use sales report from past years so that I can see requirements needed to hit specific sales margins | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
15 | As a small business owner,I want to input any date into the software so that I can review data over my company for that specific date. | F:KA |  | *Create a python process to upload the information from excel into the mysql database(backend) | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade:4 Andre: Turner: Mayur: Riggs: Carolyn:
16 | As a small business owner, I want to be able to create sub accounts, so that I can keep access to certain data restricted. | NF:KA |  | *Created account creation screen | Cade: Andre: Turner: 2 Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
17 | As a small business owner, I want to be able to log in into my account, so that I can easily access my data. | F:KA |  | *Created sign into account screen | Cade: Andre: Turner: Mayur: Riggs: Carolyn: 2 | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
18 | As a small business owner, I want to be able to set certain parameters so that i can easily view specific data | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
20 | As a small business owner I want to be able to have an unrestricted admin account to access all data | F:TW |  | *Implemented a local account database *Inputted pre-existing manager account | Cade: Andre: Turner: Mayur: 2 Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
Documentation
| SRS |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Platform |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| SprintReview |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Product Backlog |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Focus Group |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| GRL |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Domain Model and Detailed Design Model Docuent |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| CM |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Team Member Report |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:

## SprintBacklog3
ID | Story | Story Type | Story Points | Tasks | 2018-02-26 | 2018-03-05
10 | As a small business owner, I want to be able to predict the amount of sales on a certain day so that I can schedule employees accordingly | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
11 | As a small business owner,I want to be able to predict the amount of income on a certain day so that I can account for potential sales | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
12 | As a small business owner,I want to be able to input the total revenue made for the day into the database upon closing so that I can use that data to update the accuracy of the software | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
13 | As a small business owner,I want to use my sales report from past years so that I can get an estimate prediction of future sales | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
14 | As a small business owner,I want to use sales report from past years so that I can see requirements needed to hit specific sales margins | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
15 | As a small business owner,I want to input any date into the software so that I can review data over my company for that specific date. | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
16 | As a small business owner, I want to be able to create sub accounts, so that I can keep access to certain data restricted. | NF:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
17 | As a small business owner, I want to be able to log in into my account, so that I can easily access my data. | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
18 | As a small business owner, I want to be able to set certain parameters so that i can easily view specific data | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
19 | As a small business owner I want to be able to input sales reports from past years so they can be used in the application | NF:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
20 | As a small business owner I want to be able to have an unrestricted admin account to access all data | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
Documentation
| SRS |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Platform |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| SprintReview |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Product Backlog |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Focus Group |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| GRL |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Domain Model and Detailed Design Model Docuent |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| CM |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| Team Member Report |  |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:

## thoughts
ID | User Story | Story Type | Story Points | Tasks | Day 1(2/13/2018) | week 2 | Day 3 | Day 4 | Day 5
| As a small business owner, I want to be able to predict the volume of customers on a certain day so that I can schedule employees accordingly | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner,I want to be able to predict the amount of income on a certain day so that I can account for potential revenue | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner,I want to be able to input the total revenue made for the day into the database upon closing so that I can use that data to update the accuracy of the software | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner,I want to input sales report from past years so that I can get an estimate prediction of future sales | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner,I want to input sales report from past years so that I can see requirements needed to hit specific profit margins | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner,I want to input any date into the software so that I can review data over my company for that specific date. | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner, I want to be able to create an account, so that I can keep my data private. | NF:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner, I want to be able to create an account, so that I can easily access my data. | F:KA |  | Designed Account Creation Screen Designed Home Page/Linked Pages Designed Sign In Screen | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner, I want to be able to set certain parameters so that i can easily view specific data | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner I want to have a portable program so that i can access the program from multiple copmuters. | NF:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner I want to have a cross platform capable program so that I can access it on multiple Operating Systems | NF:TW |  | Code in Java to secure compatibility | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner I want to be able to input sales reports from past years so they can be used in the application | F:KA |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn:
| As a small business owner I want to be able to create sub accounts so that my employes can have restricted access | F:TW |  |  | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: | Cade: Andre: Turner: Mayur: Riggs: Carolyn: