## Mayur
Sprint 1
Week of 1/25/2018 |  | Week of 2/05/2018
Name | Mayur Bhakta | Name | Mayur Bhakta
Role | Developer | Role | Developer
Tasks performed this week | Create and update documents | Tasks performed this week | Create and update documents
Tasks to be performed this week | Update documents | Tasks to be performed this week | Update documents
Issues encountered | Properly formatting the required documents | Issues encountered | Properly formatting the required documents
Issues resolved | Properly formatting the required documents | Issues resolved | Properly formatting the required documents
Sprint 2
Week of 2/12/2018 |  | Week of 2/19/2018
Name | Mayur Bhakta | Name | Mayur Bhakta
Role | Developer | Role | Developer
Tasks performed this week | Update documentations | Tasks performed this week | Created login, account creation, home page screens.
Tasks to be performed this week | Created login, account creation, home page screens. | Tasks to be performed this week | Continue creating and updating screens as needed.
Issues encountered | Proper formatting | Issues encountered | Linking screens together
Issues resolved | Proper formatting | Issues resolved | Linking screens together
Sprint 3
Week of 2/26/2018 |  | Week of 3/05/2018
Name | Mayur Bhakta | Name | Mayur Bhakta
Role | Scrum Master | Role | Scrum Master
Tasks performed this week | Assigned task to team members, and worked on new documents for deliverable 2. | Tasks performed this week
Tasks to be performed this week | Clean up GUI, continue updating front end. | Tasks to be performed this week
Issues encountered | Some disagreements between members about the use cases | Issues encountered
Issues resolved | Some disagreements between members about the use cases | Issues resolved
Sprint 4
Week of |  | Week of
Name | Mayur Bhakta | Name | Mayur Bhakta
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 5
Week of |  | Week of
Name | Mayur Bhakta | Name | Mayur Bhakta
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 6
Week of |  | Week of
Name | Mayur Bhakta | Name | Mayur Bhakta
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved

## Andre
Sprint 1
Week of 1/25/2018 |  | Week of 2/05/2018
Name | Andre Manz | Name | Andre Manz
Role | Manager | Role | Manager
Tasks performed this week | Use case diagrams/Documentation | Tasks performed this week | Documentation/SRS
Tasks to be performed this week | Retrieve client data | Tasks to be performed this week | Update documentation
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 2
Week of 2/12/2018 |  | Week of 2/19/2018
Name | Andre Manz | Name | Andre Manz
Role | Scrum Master | Role | Scrum Master
Tasks performed this week | Updated Documentation/SRS | Tasks performed this week | Refined Encryption Updated Documentation/SRS
Tasks to be performed this week | AES Encryption of Passwords | Tasks to be performed this week | Update Documentation
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 3
Week of 2/26/2018 |  | Week of
Name | Andre Manz | Name | Andre Manz
Role | Developer | Role
Tasks performed this week | Updated and clarified Documentation | Tasks performed this week
Tasks to be performed this week | Update Documentation, Work on encryption | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 4
Week of |  | Week of
Name | Andre Manz | Name | Andre Manz
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 5
Week of |  | Week of
Name | Andre Manz | Name | Andre Manz
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 6
Week of |  | Week of
Name | Andre Manz | Name | Andre Manz
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved

## Riggs
Sprint 1
Week of 1/25/2018 |  | Week of 2/05/2018
Name | Aaron Riggs | Name | Aaron Riggs
Role | Developer | Role | Developer
Tasks performed this week | back end encryption discussion. | Tasks performed this week | working on the SRS and Team member report.
Tasks to be performed this week | Start With python encryption. | Tasks to be performed this week | back end encryption implementation and updating documentation.
Issues encountered | Python on windows having issues with mySQL | Issues encountered | getting team members to inform for documentation
Issues resolved | N/A | Issues resolved | Python working withg mySQL
Sprint 2
Week of 2/12/2018 |  | Week of 2/19/2018
Name | Aaron Riggs | Name | Aaron Riggs
Role |  | Role
Tasks performed this week | back end encryption completed in Python. | Tasks performed this week | Started the conversion from python to java
Tasks to be performed this week | back end encryption implementation. | Tasks to be performed this week | Convert back end encryption software to java from python to better integrate with the front end team
Issues encountered | Python integration issues with the front end team. | Issues encountered | the way that java handles strings is destroying the encryption data, Java was having trouble reaching the mySQL server.
Issues resolved | Python encryption working withg mySQL | Issues resolved | Was able to fix java's connection to the mySQL server
Sprint 3
Week of |  | Week of
Name | Aaron Riggs | Name | Aaron Riggs
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 4
Week of |  | Week of
Name | Aaron Riggs | Name | Aaron Riggs
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 5
Week of |  | Week of
Name | Aaron Riggs | Name | Aaron Riggs
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 6
Week of |  | Week of
Name | Aaron Riggs | Name | Aaron Riggs
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved

## Turner
Sprint 1
Week of 1/25/2018 |  | Week of 2/05/2018
Name | Aaron Turner | Name | Aaron Turner
Role | Developer | Role | Developer
Tasks performed this week | create and update documents | Tasks performed this week | create and update documents
Tasks to be performed this week | create and update documents | Tasks to be performed this week | create and update documents
Issues encountered | properly formatting the required documents | Issues encountered | properly formatting the required documents
Issues resolved | properly formatting the required documents | Issues resolved | properly formatting the required documents
Sprint 2
Week of 2/12/2018 |  | Week of 2/19/2018
Name | Aaron Turner | Name | Aaron Turner
Role | Developer | Role | Developer
Tasks performed this week | More documentation | Tasks performed this week | Created account creation screen
Tasks to be performed this week | More documentation | Tasks to be performed this week | Create account creation screen
Issues encountered | Proper formatting | Issues encountered | Linking screens together
Issues resolved | Proper formatting | Issues resolved | Linking screens together
Sprint 3
Week of 2/26/2018 |  | Week of 3/05/2018
Name | Aaron Turner | Name | Aaron Turner
Role | Developer | Role
Tasks performed this week | Cleaned up GUI and reconciled screen inconsistencies and updated scrum backlog | Tasks performed this week
Tasks to be performed this week | Clean up GUI and reconcile screen inconsistencies and update scrum backlog | Tasks to be performed this week
Issues encountered | Out of date info and inconsistencies | Issues encountered
Issues resolved | Out of date info and inconsistencies | Issues resolved
Sprint 4
Week of |  | Week of
Name | Aaron Turner | Name | Aaron Turner
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 5
Week of |  | Week of
Name | Aaron Turner | Name | Aaron Turner
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 6
Week of |  | Week of
Name | Aaron Turner | Name | Aaron Turner
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved

## Cade
Sprint 1
Week of 1/25/2018 |  | Week of 2/5/2018
Name | Cade Wall | Name | Cade Wall
Role | Sprint Leader | Role
Tasks performed this week | create and update documents | Tasks performed this week | create and update documents
Tasks to be performed this week | create and update documents | Tasks to be performed this week | create and update documents
Issues encountered | properly formatting the required documents | Issues encountered | properly formatting the required documents
Issues resolved | properly formatting the required documents | Issues resolved | properly formatting the required documents
Sprint 2
Week of 2/12/2018 |  | Week of 2/19/2018
Name | Cade Wall | Name | Cade Wall
Role | Developer | Role | Developer
Tasks performed this week | create a python file that read in input from a excel csv file then formated as to input daily information table to then fill the months tables. | Tasks performed this week | translate python code into java. Completed reading from daily information table and doing proper calculations to fill out the months table. Reading from excel csv not implemented.
Tasks to be performed this week | create a python file to read in input from an excel coverted csv file then upload it to the database with schema sales data and fill out dailyinformation table. On upload also do calculations to fill smaller tables then proceede to fill smaller tables | Tasks to be performed this week | Fix python to upload into the daily information table
Issues encountered | Finding a proper python library for the ablility to connect to mysql inserting information into the daily information table | Issues encountered | Entering data into the daily information table via python
Issues resolved | Finding a proper python library for the ablility to connect to mysql | Issues resolved | Entering data into the daily information table via python.(solved by changing languages)
Sprint 3
Week of |  | Week of
Name | Cade Wall | Name | Cade Wall
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 4
Week of |  | Week of
Name | Cade Wall | Name | Cade Wall
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 5
Week of |  | Week of
Name | Cade Wall | Name | Cade Wall
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 6
Week of |  | Week of
Name | Cade Wall | Name | Cade Wall
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved

## Xujia
Sprint 1
Week of 1/25/2018 |  | Week of 2/05/2018
Name | Xujia Wu | Name | Xujia Wu
Role | developer | Role | developer
Tasks performed this week | create and update documents | Tasks performed this week | create and update documents
Tasks to be performed this week | create and update documents | Tasks to be performed this week | create and update documents
Issues encountered | properly formatting the required documents | Issues encountered | properly formatting the required documents
Issues resolved | properly formatting the required documents | Issues resolved | properly formatting the required documents
Sprint 2
Week of 2/12/2018 |  | Week of 2/19/2018
Name | Xujia Wu | Name | Xujia Wu
Role | developer | Role | developer
Tasks performed this week | Update documentations | Tasks performed this week | Created login screen.
Tasks to be performed this week | Created login, account creation, home page screens. | Tasks to be performed this week | Created login screen.
Issues encountered | Proper formatting | Issues encountered | Linking screens together
Issues resolved | Proper formatting | Issues resolved | Linking screens together
Sprint 3
Week of 2/26/2018 |  | Week of
Name | Xujia Wu | Name | Xujia Wu
Role | developer | Role | developer
Tasks performed this week | Cleaned up GUI and Create GRL and UCM Models document. | Tasks performed this week
Tasks to be performed this week | Cleaned up GUI and Create GRL and UCM Models document. | Tasks to be performed this week
Issues encountered | how to create GRL and UCM correctly | Issues encountered
Issues resolved | create GRL and UCM correctly | Issues resolved
Sprint 4
Week of |  | Week of
Name | Xujia Wu | Name | Xujia Wu
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 5
Week of |  | Week of
Name | Xujia Wu | Name | Xujia Wu
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved
Sprint 6
Week of |  | Week of
Name | Xujia Wu | Name | Xujia Wu
Role |  | Role
Tasks performed this week |  | Tasks performed this week
Tasks to be performed this week |  | Tasks to be performed this week
Issues encountered |  | Issues encountered
Issues resolved |  | Issues resolved